## Sheet1
Task | Files Required | Team Member | Date | Final Review | Next Team Meeting on 10/22/2020
TEST CASE TABLES
Registration (Passenger) | User.java attributes.xls UCID Sirs example of Test cases | Parakh Naman | 2020-10-22 | Vratant
Login (Passenger, CM, Event Manager) | User.java attributes.xls UCID Sirs example of Test cases | Parakh Naman |  | Vratant
Update Profile (Passenger) | User.java attributes.xls UCID Sirs example of Test cases | Parakh Naman |  | Vratant
Search Event (Date/Time) (CM, Event Manager) | Event.java attributes.xls UCID Sirs example of Test cases | Amey Kavya |  | Nigel
Search All Event (Date/Time) (Passenger) | Event.java attributes.xls UCID Sirs example of Test cases | Amey Kavya |  | Nigel
Search Reservation (Date/Time) (Passenger) | Event.java attributes.xls UCID Sirs example of Test cases | Amey Kavya |  | Nigel
Modify Event (Event Manager) | Event.java attributes.xls UCID Sirs example of Test cases | Amey Kavya |  | Nigel
PROJECT CODE CHANGES
User.java ¦ UserErrormsgs.java | Nigel | Nigel | 2020-10-22 | Vratant
Event.java ¦ EventErrormsgs.java | Nigel | Nigel |  | Vratant
Reservation.java ¦ ReservationErrormsgs.java | Nigel | Nigel |  | Vratant
JUNIT TEST CASES CODING & RESULTS
Registration (Passenger) | Parakh Naman Vratant |  | 2020-10-25 | Vratant
Login (Passenger, CM, Event Manager) | Parakh Naman Vratant |  |  | Vratant
Update Profile (Passenger) | Parakh Naman Vratant |  |  | Vratant
Search Event / Reservation (Date/Time) (CM, Event Manager) | Amey Kavya Nigel |  |  | Nigel
Search All Event / Reservation (Date/Time) (Passenger) | Amey Kavya Nigel |  |  | Nigel
Search Reservation (Date/Time) (Passenger) | Amey Kavya Nigel |  |  | Nigel
Modify Event (Event Manager)
JACOCO TEST CASES CODING & RESULTS
Registration (Passenger) | Parakh Naman Vratant |  | 2020-10-25
Login (Passenger, CM, Event Manager) | Parakh Naman Vratant
Update Profile (Passenger) | Parakh Naman Vratant
Search Event / Reservation (Date/Time) (CM, Event Manager) | Amey Kavya Nigel
Search All Event / Reservation (Date/Time) (Passenger) | Amey Kavya Nigel
Search Reservation (Date/Time) (Passenger) | Amey Kavya Nigel
Modify Event (Event Manager) | Amey Kavya Nigel
PIT TEST CASES CODING & RESULTS
Registration (Passenger) | Parakh Naman Vratant |  | 2020-10-26
Login (Passenger, CM, Event Manager) | Parakh Naman Vratant
Update Profile (Passenger) | Parakh Naman Vratant
Search Event / Reservation (Date/Time) (CM, Event Manager) | Amey Kavya Nigel
Search All Event / Reservation (Date/Time) (Passenger) | Amey Kavya Nigel
Search Reservation (Date/Time) (Passenger) | Amey Kavya Nigel
Modify Event (Event Manager) | Amey Kavya Nigel
DOCUMENTATION
Team1_TestReport | Naman |  | 2020-10-27
A03 Test Results Summary Table | Parakh
Team1-TeamMembersTasks | Amey
Folder Organization / Naming | Amey
Usage check validation mapping | Vratant
YOUTUBE VIDEO FINAL |  |  | 2020-10-28